## Summary
StepIn: development test report
Project | StepIn — ticketed event page (Payload CMS + Stripe Checkout sandbox), deployed at https://stepin-virid.vercel.app
Period | 2026-10-19, from first build to Phase 1 (bookings and tables) and its final code review
Environments | Local (Neon branch dev), Vercel production (Neon branch main), Stripe sandbox (test keys only)
Kinds of test | Manual browser checks (Playwright), automated unit and integration tests (Vitest), mutation checks, code reviews by AI reviewers, migration rehearsals on throwaway database branches
Sheets | "Development tests" lists every issue and check with its fix; "Automated test suite" lists each automated test
Counts
Development checks
Fixed
Passed first time
Not reproducible
Known issues (open)
Automated tests
Automated tests passing
Unit tests
Integration tests

## Development tests
StepIn: development tests and fixes
Every check run while building StepIn (2026-10-19): what it tested, the first outcome, what was done, and the outcome after the fix.
ID | Area | Test / check | What it tested | Outcome (first run) | What was done to resolve | Outcome after fix | Status
D-01 | Secrets | Review of .env.example before first commit | That no real key is committed to the repository. | Fail: the real sandbox secret key (sk_test_…) had been typed into .env.example, a tracked file. | Moved the key into .env (git-ignored) and restored the placeholder before anything was committed. | Pass: a scan of the whole git history on every branch finds no Stripe key, webhook secret, database password or Blob token. | Fixed
D-02 | Payment | Manual end-to-end purchase (first checkout build) | Checkout reaches Stripe with the server price; signed webhook marks the order paid; repeat delivery changes nothing; bad signature refused. | Pass: 2 × VIP = €120.00 at Stripe; bad signature → 400; event delivered twice → order paid once. | None needed. | Pass | Pass
D-03 | Admin | Event slug when the same event is repeated | That a second "Mandjiedans" on a new date can be saved. | Fail: "Value must be unique" — the slug was the name only. | Slug is now name + date (e.g. mandjiedans-2026-10-31), set by a custom slugify on the Events collection. | Pass: tested with a temporary draft event (slug mandjiedans-2026-10-31); confirmed by the owner in the admin. | Fixed
D-04 | Local setup | Opening /admin locally | That the admin panel loads. | Fail: "Jest worker encountered 2 child process exceptions" — a leftover test server whose workers had been stopped. | Stopped the broken server process and started a fresh dev server. | Pass: admin loads. | Fixed
D-05 | Local setup | stripe listen for local webhooks | That Stripe CLI forwards webhooks to the local app. | Fail: CLI 1.54 refuses to start without an event list. | Start it with --events checkout.session.completed,checkout.session.async_payment_succeeded (documented in README). | Pass: test event delivered, webhook answered 200 with the verified secret. | Fixed
D-06 | Layout | Upcoming events list height | Event cards half their height so more fit on a screen. | Fail: cards 182 px tall; without an image the text was squeezed into the image column. | Cards rebuilt as one flex row; shorter date format. | Pass: 67 px per card on a laptop (1366×768), 90 px on a phone (390×844). | Fixed
D-07 | Layout | Event page fits one screen | Buy button visible without scrolling, even with a large image and long description. | Fail (worst case): on a phone a long description pushed the buy box below the screen. | Two columns on wide screens (details ¦ sticky buy box); on phones the buy box comes before the description. | Pass: buy button bottom at 269/768 px (laptop) and 586/844 px (phone). | Fixed
D-08 | Admin layout | Event form fits one screen | The whole admin event form visible without scrolling. | Fail: needed scrolling. | Image moved to the sidebar, ticket name and price side by side, shorter description box, price hint moved into the label. | Pass: last field at 648/740 px on the owner's screen size. | Fixed
D-09 | Admin layout | Admin form cut off on the right | That the form fits the browser width. | Fail: right column cut off. | Cause was the test browser tab being left at a 1920 px emulated width by an earlier check; reset the tab to the window size. No code change. | Pass: confirmed by the owner. | Fixed
D-10 | Code review (ai-architect) | Home page event list | All upcoming events are listed. | Fail: Payload returns 10 results by default, so an 11th event would never show. | pagination: false and a select of only the needed fields. | Pass | Fixed
D-11 | Code review (ai-architect) | Sticky buy box on phones | The buy box stops being sticky on narrow screens. | Fail: the phone rule came before the main rule in the CSS, so it never applied. | Moved the phone media query after the main rules. | Pass | Fixed
D-12 | Code review (ai-architect) | Checkout event lookup | No duplicated lookup logic. | Finding: the slug lookup was repeated in the page and in checkout; an idempotency key did nothing. | Checkout looks the event up by id; removed the useless idempotency key; webhook and success page load less data. | Pass: checkout reached Stripe with the right amount. | Fixed
D-13 | Deploy | Production build (npm run build) | That the app builds for Vercel. | Pass | None needed. | Pass on every phase (also after each fix below). | Pass
D-14 | Deploy | First Vercel deployment | That the PR branch deploys as a preview. | Unexpected: Vercel makes a project's first deployment production, so the PR branch went live first. | Confirmed the production branch is main; merging the PR redeployed production from main. | Pass: production serves main (stepin-virid.vercel.app). | Fixed
D-15 | Database | Separate dev and production databases | That local work no longer touches live data and that migrations are a no-op on production. | Pass | Neon branch "dev" for local and previews; baseline migration marked applied on main; rehearsed on a throwaway branch of main first. | Pass: payload migrate on a copy of production reports nothing to run. | Pass
D-16 | Seating | Seat counting with more than 10 bookings | Every booking is counted even past Payload's 10-per-page default. | Pass (mutation check: removing pagination:false makes the test fail with 9 instead of 6). | None needed. | Pass | Pass
D-17 | Seating | Adding a guest to an existing party | Newcomers are auto-seated only when the whole party was cancelled (old app's rule). | Fail: a guest added to a party the owner was seating by hand was auto-seated. | Rule changed to "party had no live guests", matching the old app spec. | Pass | Fixed
D-18 | Checkout | Two buyers for the last seats at the same moment | Only one of two simultaneous buyers can take the last seats. | Pass (mutation check: without the per-event lock both buyers got the seats in 3 of 3 runs). | None needed. | Pass | Pass
D-19 | Checkout | Stripe session expiry | Seat hold and Stripe payment page expire together. | Fail (design): Stripe refuses a page that expires less than 30 minutes after creation, and the hold starts seconds earlier. | Hold set to 31 minutes; Stripe expires_at = hold end. | Pass | Fixed
D-20 | Webhook | Booking creation fails during the webhook | Stripe retries instead of leaving a paid order without a booking. | Fail: Payload's bulk update reports failures in a list instead of throwing, so the route answered 200. | Route throws when the update reports errors (Stripe then retries). | Pass: test RED against the old route, GREEN after. | Fixed
D-21 | Webhook | Booking fails for a non-database reason (final review) | Order stays pending so a retry can still create the booking. | Not reproducible: a failing booking save rolls back Payload's whole transaction, so the order stays pending. | Kept a guard test (booking with an invalid price) instead of changing code. | Pass | Not reproducible
D-22 | Validation | Price minimums | Guest price ≥ 0; ticket price ≥ 50 cents (Stripe minimum). | Fail: a custom price check replaced Payload's own minimum check, so −5 and 10 cents were accepted. | Custom checks now enforce the minimums themselves. | Pass: test RED → GREEN. | Fixed
D-23 | Seating | Two bookings saved at the same moment (final review) | Automatic seating never puts more guests at a table than it has seats. | Fail: 4 guests seated at a 3-seat table. | Automatic seating takes the same per-event lock as checkout (shared lockEvent helper). | Pass: 3 of 3 runs. | Fixed
D-24 | Payment | Two ticket types with the same name, different prices (final review) | Stripe's total always equals the order amount. | Fail: Stripe lines grouped by name only → €20.00 charged for a €25.00 order. | Stripe lines grouped by name and price. | Pass: test RED → GREEN. | Fixed
D-25 | Admin | Deleting an event that has bookings (final review) | Event can be deleted; its bookings go with it; its orders are kept. | Fail: raw database error (not-null violation) — a regression from Phase 1. | Events beforeDelete hook deletes the event's bookings first. | Pass: event with 12 bookings deleted, order kept with event name. | Fixed
D-26 | Layout | Event page with the new guest form | Description directly under the event details. | Fail: the taller buy form stretched the grid row and pushed the description ~200 px down. | grid-template-rows: auto 1fr. | Pass: 12 px gap. | Fixed
D-27 | Success page | Wording for mixed tickets | Readable summary after payment. | Fail: "3 × Standard ×3". | Reads "3 tickets (Standard ×3) for Mandjiedans". | Pass | Fixed
D-28 | Database | Phase 1 migration on a copy of production | New tables, order event names backfilled, existing paid order turned into a booking. | Pass: only the Phase 1 migration ran; 2 orders got their event name; paid order → booking "Guest 1". | None needed (throwaway branch deleted). | Pass | Pass
D-29 | Tooling | npm run lint | That ESLint runs. | Fail: config error from the Payload template. | Not fixed (template issue, does not affect build or tests). | Open | Known issue

## Automated test suite
StepIn: automated test suite (npm test)
Final run on branch phase-1-bookings, 2026-10-19: 14 unit tests + 26 integration tests against the Neon dev branch. Integration tests create and delete their own data.
Test file | Type | Test name | What it checks | Result
tests/unit/seating.spec.ts | Unit | lays out a new room in plan order | Plan lines become numbered tables in order. | Pass
tests/unit/seating.spec.ts | Unit | keeps the lowest-numbered tables when the room shrinks | Shrinking keeps tables 1..n and lists the dropped ones. | Pass
tests/unit/seating.spec.ts | Unit | numbers new tables past the highest ever used | Table numbers are never reused. | Pass
tests/unit/seating.spec.ts | Unit | drops every table for a plan of nought tables | Nought tables means the room is not laid out. | Pass
tests/unit/seating.spec.ts | Unit | ignores cancelled and unseated guests | Only live, seated guests take seats. | Pass
tests/unit/seating.spec.ts | Unit | picks the tightest table the party still fits | Old app rule: least room to spare that still fits. | Pass
tests/unit/seating.spec.ts | Unit | breaks ties on the lower table number | Predictable choice. | Pass
tests/unit/seating.spec.ts | Unit | splits a party too large for any table across the closest run | Split seating, at least 2 per table. | Pass
tests/unit/seating.spec.ts | Unit | returns null when no arrangement seats the whole party | Whole party or nobody. | Pass
tests/unit/seating.spec.ts | Unit | has no limit when no tables are laid out | No table plan = no seat limit. | Pass
tests/unit/seating.spec.ts | Unit | subtracts live and held guests from the room | Seats left = room − guests − held seats. | Pass
tests/unit/seating.spec.ts | Unit | never goes below nought | An over-full room shows 0, not negative. | Pass
tests/unit/stripe-lines.spec.ts | Unit | groups guests into one line per ticket type | Stripe shows "VIP × 2" style lines. | Pass
tests/unit/stripe-lines.spec.ts | Unit | keeps two ticket types with the same name but different prices apart, so the total matches | Stripe total always equals the order (D-24). | Pass
tests/int/api.int.spec.ts | Integration | fetches users | Payload starts and reads the database (template test). | Pass
tests/int/bookings.int.spec.ts | Integration | needs a telephone for a phone booking but not for an online one | Telephone rule per booking source. | Pass
tests/int/bookings.int.spec.ts | Integration | seats a new party together at the tightest table | Automatic seating on a new booking. | Pass
tests/int/bookings.int.spec.ts | Integration | cancelling one guest gives the seat back | Cancel part of a booking. | Pass
tests/int/bookings.int.spec.ts | Integration | cancelling the whole booking cancels and unseats every guest | Cancel whole booking. | Pass
tests/int/bookings.int.spec.ts | Integration | marks a party with a live unseated guest | "Needs seating" flag. | Pass
tests/int/bookings.int.spec.ts | Integration | seats a guest added to a party that sits nowhere, but not one placed by hand | Newcomer rule (D-17). | Pass
tests/int/bookings.int.spec.ts | Integration | refuses to drop a table with guests at it until confirmed, then unseats them | Table-plan shrink needs Confirm. | Pass
tests/int/bookings.int.spec.ts | Integration | refuses a negative guest price and a ticket price under 50 cents | Price minimums (D-22). | Pass
tests/int/bookings.int.spec.ts | Integration | never seats two parties saved together beyond the table size | Seating lock (D-23). | Pass
tests/int/bookings.int.spec.ts | Integration | takes its bookings with it and keeps its orders | Event delete (D-25), 12 bookings. | Pass
tests/int/event-seats.int.spec.ts | Integration | counts every booking, cancellations and live seat holds | Seat count past 10 bookings (D-16); expired holds ignored. | Pass
tests/int/event-seats.int.spec.ts | Integration | has no limit when the room is not laid out | No plan = no limit. | Pass
tests/int/event-tables.int.spec.ts | Integration | publishing stores the tables the plan describes | Plan → tables on publish. | Pass
tests/int/event-tables.int.spec.ts | Integration | a draft save leaves the published tables alone until it is published | Drafts never change the live room. | Pass
tests/int/order-to-booking.int.spec.ts | Integration | creates one seated booking of paid guests | Paid order → booking. | Pass
tests/int/order-to-booking.int.spec.ts | Integration | a repeated delivery creates no second booking | Webhook idempotency (sequential). | Pass
tests/int/order-to-booking.int.spec.ts | Integration | two deliveries at the same moment create one booking | Webhook idempotency (concurrent). | Pass
tests/int/order-to-booking.int.spec.ts | Integration | leaves a party that fits nowhere unseated and marked | Oversized party stays unseated. | Pass
tests/int/reserve-seats.int.spec.ts | Integration | holds the seats on a pending order priced from Payload | Server-side prices, 31-min hold, event name copied. | Pass
tests/int/reserve-seats.int.spec.ts | Integration | refuses tampered or impossible requests | 11 guests, empty names, foreign ticket, draft/past event, bad id → no order. | Pass
tests/int/reserve-seats.int.spec.ts | Integration | refuses more guests than seats left | Sold out message. | Pass
tests/int/reserve-seats.int.spec.ts | Integration | lets only one of two simultaneous buyers take the last seats | Per-event lock (D-18). | Pass
tests/int/webhook.int.spec.ts | Integration | marks the order paid and creates its booking with the phone number | Signed webhook end to end. | Pass
tests/int/webhook.int.spec.ts | Integration | answers with an error when the booking cannot be created, so Stripe retries | D-20. | Pass
tests/int/webhook.int.spec.ts | Integration | keeps the order pending when the booking fails validation, so a retry can still book it | D-21 guard. | Pass